## SUB
Status | Address | Developer | Planning Ref Number | Date of Legal Agreement | Ward | Proposal Summary | Category | Sub-Category | Amount Secured (not including indexation) | No's | Obligation Detail | Trigger | Terms | Update
Secured | Wood Farm Holdings Stanton Lane SUB | Wood Farm Holdings / Oxalis | 21/00531/HYB APP/K2420/W/21/3279939 23/00080/REM | 2021-11-01 | Stanton Under Bardon | Outline- erection buildings for storage and distribution uses (Class B8), general industry (Class B2) FUL -demolition of existing farm replacement 2 x farm managers dwellings | On Site POS | Community Facility |  |  | Community Open Space to be provided on site (shown as green on the plan) including footpath for connectivity | Prior to 1st occupation of the 1st unit to implement during construction of the development - probably need imp plan | Community Open Space | No occupation as of September 2025
Secured | Wood Farm Holdings Stanton Lane SUB | Wood Farm Holdings / Oxalis | 21/00531/HYB APP/K2420/W/21/3279939 | 2021-11-01 | Stanton Under Bardon | Outline- erection buildings for storage and distribution uses (Class B8), general industry (Class B2) FUL -demolition of existing farm replacement 2 x farm managers dwellings | On Site POS | Landscape Management Plan |  |  | Community Open Space Management Plan | Prior to 1st occupation of the 1st unit |  | Some conditions have been discharged
Secured | Land South of Main Street | K P Richardson Allison Homes | 22/00527/OUT 24/00828/REM | 2024-06-21 | Stanton Under Bardon | 50 Dwellings | On Site POS | Accessible Green Space Provision |  | 1 | Identify what Accessible Natural Green Space is | To be Agreed at REM Stage | Policy requirement | Starting on site Autumn 2025
Secured | Land South of Main Street | K P Richardson Allison Homes | 22/00527/OUT 24/00828/REM | 2024-06-21 | Stanton Under Bardon | 50 Dwellings | On Site POS | Equipped Provision | 32747.4 | 1 | Equipment to the value of 32747.40 plus indexation | At stage of submitting equipped details REM/Prior to commencement | To be ocnfirmed when submitting Play equipment plan | Starting on site Autumn 2025
Secured | Land South of Main Street | K P Richardson Allison Homes | 22/00527/OUT 24/00828/REM | 2024-06-21 | Stanton Under Bardon | 50 Dwellings | On Site POS | Equipped Maintenance | 31608 |  | Maintennace Sum if transferred to to the Parish | Only payable on transfer of open space to a P C or BC |  | Starting on site Autumn 2025
Secured | Land South of Main Street | K P Richardson Allison Homes | 22/00527/OUT 24/00828/REM | 2024-06-21 | Stanton Under Bardon | 50 Dwellings | On Site POS | Accessible Green Space Maintenance | 9072 |  | Maintennace Sum if transferred to to the Parish | Only payable on transfer of open space to a P C or BC |  | Starting on site Autumn 2025
Secured | Land South of Main Street | K P Richardson Allison Homes | 22/00527/OUT 24/00828/REM | 2024-06-21 | Stanton Under Bardon | 50 Dwellings | On Site POS | Accessible Green Space Maintenance | 28400 |  | Maintennace Sum if transferred to Bor Parish | Only payable on transfer of open space to a P C or BC |  | Starting on site Autumn 2025
Secured | Land South of Main Street | K P Richardson Allison Homes | 22/00527/OUT 24/00828/REM | 2024-06-21 | Stanton Under Bardon | 50 Dwellings | On Site POS | Maintenance |  |  | Scheme for the future maintenance | At time of Developer deciding to transfer to the parish or not |  | Starting on site Autumn 2025
Secured | Land South of Main Street | K P Richardson Allison Homes | 22/00527/OUT 24/00828/REM | 2024-06-21 | Stanton Under Bardon | 50 Dwellings | Off Site POS | Outdoor Sports Provision | 17376 |  | Provision sum | Prior to commencement | STA05 Towards the outdoor sports provision / improvments and or maintenance of the outdoor sports improvements / facilities at SUB Recreation Ground | Due to be invoiced September 25
Secured | Land South of Main Street | K P Richardson Allison Homes | 22/00527/OUT 24/00828/REM | 2024-06-21 | Stanton Under Bardon | 50 Dwellings | Off Site POS | Outdoor Sports Maintenance | 8256 |  | Maintenance Sum | Prior to 50% occupation | Maitneance of the provision