## Sheet1
Policy Action Area | Action | Benefit/Outcome | Target Date |  | Progress | Reporting/Publicity
Local community | Identify local community groups we can approach to support/aid biodiversity. | No cost. Identify community support for biodiversity improvements. | 2024-09-16 |  | To be started | PC minutes
Planning Applications | Consider adopting SLCC 'Commenting on Local Planning Applications Guidance in respect of climate change April 2024' Appendix 7 in relation to biodiversity | No cost. Useful tool to aid planning decisions with biodiversity in mind. | 2024-09-16 |  | To be started | Planning minutes to document 'Points to check in planning application' going forward.
Land and property management | PC to consider making it Parish policy not to use any herbicides or pesticides on land they own or manage. | No cost. Increased biodiversity. Improve resilience of nature. | 2024-10-21 | All | To be started | PC minutes, Biodiversity policy
Land and property management | Review maintenance management of Jubilee and Memorial fields, including cutting, application of chemicals and timing of maintenace work. | No cost. Ensures maintenace work has minimal impact on nature and habitat. | 2024-10-21 | Helen/Kate S | To be started | PC minutes
Land and property management | Identify any areas at the Jubilee and Memorial fields where we can provide homes for nature eg nest boxes, log piles, insect hotels. | No cost. Identify any areas where we can provide homes for wildlife and increase habitat. | 2024-10-30 | Kate S | To be started | PC minutes
Local community | Litter picking: 1. Consider restarting community annual litter picking event. 2. Ask the community whether individuals would like to take ownership of litter picking on a particular roads/areas | No cost. Improved habitat condition for wildlife. Fewer wildlife deaths from litter. Improved mental health . Safer public open space. Improved resilience of nature. | 2024-12-31 |  | To be started | Publicise dates on Facebook and via community email group
Partners | Install dog poo bin in Badgworth | Protecting habitat | 2024-12-31 | Helen | In progress | PC minutes and Badgworth email group
Local community | Communicate to encourage the community to not mow their verges and plant wildflowers. | No cost. Increase habitat for wildlife. Increased biodiversity. | 2025-03-01 | Helen/Kate S | To be started | Facebook, community email groups
Local community | Communicate to encourage the community to take part in No Mow April/May. | No cost. Increase habitat for wildlife. Increase biodiversity. Increase community awareness. | 2025-03-01 | Helen/Kate S | To be started | Facebook, community email groups
Local community | Communicate that it is the start of bird nesting season. | No cost. Increase community awareness. Protecting habitat. | 2025-03-01 | Helen/Kate S | To be started | PC Facebook, community emails
Land and property management | During annual budget planning, consider having a budget for biodiversity work. | Low cost. Provide funding to increase habitat/biodiversity. |  | All | To be started | PC budget/minutes
Local community | Review the need for litter picking equipment, do we need to consider in the next budget? | Provide tools for the community to use. |  |  | To be started | PC budget/minutes
Local community | Consider ways the Jubiliee and Memorial fields can be made more biodiverse. Present options to the PC. | No cost. Identify an area where we can increase habitat. |  | Kate S | To be started
Local community | Work with local community groups to identify homes for nature eg nest boxes, log piles | Increase habitat for wildlife. Increase community engagement

## Sheet2
Policy Action Area
Planning Applications
Land and property management
Local community
Partners
Progress
To be started
In progress
Complete
Ongoing
Pending
Benefit/Outcome
Community engagement
Cost - low
Cost - high
Cost - medium
Improved habitat/wildlife
Improved mental health
Less wildlife injuries/deaths
Increased habitat/wildlife
Protect habitat/wildlife