## Intro
Colwinston Old Ford Project (COFP) - Introduction
The Colwinston Old Ford Project operates under the Colwinston Community Council / Cyngor Cymuned Tregolwyn.
Project Summary
Adoption and restoration of an ancient woodland and adjacent wetland area, in order to: create and sustain an important community asset, restore an ecological site now at further risk from climate change, create a learning resource for village residents and especially local schoolchildren, and connect with ongoingheritage projects in the immediate area of the woodland.For many years, the site has been an informal recreational area for the community. It also has a long history in the village, as the boundaries of the ancient woodland are, for example, visible in historic tithe maps from the early 19th century. The Community Council, building on the success of the bridge and well projects, now wishes to develop this site to conserve and enhance it for recreational purposes, for learning projects for local schoolchildren and residents, and also to protect the wildlife, the trees and the local flora and fauna. The area can become a thriving natural environment, with the bridge and well as its focal points, and a valuable recreational and community resource for both current and future generations.
COFP Working Party Members:
|  | Ed Lewis (CCC councilor & Project Lead) |  | Dale Cleaver (Project Manager) | Richard Gibb
|  | Brian Morris (CCC councilor & Project Treasurer) |  | Rhian Cleaver | Cynthia Gibb
|  | Carl Hadley (CCC councilor) |  | Julia Olson | Noni Bates
|  | Julie Lloyd (CCC councilor) |  | Clive Francis | Kevin Protheroe (Clerk to the CCC)
Plan Outline:
| 1) | The Vale Ecologist (Colin Cheesman) described a zonal approach and five separate zones have been identified because the requirements for each could be progressed in isolation of each other:
|  | Zone A - | 'Woodland' is the wooded area south of Colwinston Brook on the right-hand side of the road leaving the village.
|  | Zone B - | 'Wetland' is the area between the Colwinston Brook, the ancient well and the farmer's track that borders the 'Woodland' on the right-hand side of the road leaving the village.
|  | Zone C - | 'Hedge Path' is the strip of land on in between the tributary stream that borders zones B and C and the farmer's hedge and was identified as a possible pathway.
|  | Zone D - | 'Michaelmas Well' is just before Zone C (nearer the village) on the right-hand side of the road leaving the village.
|  | Zone E - | 'Clapper Bridge' is the straddles the Colwinston Brook on the left-hand side of the road leaving the village.
| 2) | The following plan is intended to provide an initial structured view of the tasks suggested by the Vale Council Ecologist to enable the 'Colwinston Old Ford Project Working Party' to discuss and agree next steps e.g. priorities, task ownership, timelines and resource.

## Overview Map
Colwinston Old Ford Project (COFP) - Overview Maps
|  |  | Key: | Highway | Verge
| Source: VoG (OS Maps) | Source: VoG (OS Maps) | Source: VoG (OS Maps)
Zone D - Ancient Well
Zone E - Clapper Bridge
Zone A - Woodland
Zone C - Hedge
Zone B - Wetland

## HL Designs
Colwinston Old Ford Project (COFP) - High Level Designs
Some of the initial designs are included below for context.
New Perimeter/Retaining Wall
Join
Stile
New
Slabs
The Old Ford Pond, Colwinston
Vision
To create a community open space area centred on the Old Ford, offering a mix of ‘outdoor rooms’ that provide spaces for residents to rest, relax, and play. A variety of seating/open spaces should be designed to appeal to a range of users, with each ‘lily-pad’ having its own feel, character and function. The Old Ford community space
will also aim to provide essential habitat for wildlife, including providing enhanced hedgerow buffers, new tree planting, native wetland, marginal plantings, and wildflowers to encourage pollinators, insects, and wildlife. The range of habitats accomodated improve the biodiversity
of the space and also offer an opportunity for residents to get close to nature, improving health and wellbeing.
New trees such as native willows planted to create shade and interest and to provide a canopy over the ‘outdoor rooms’.
Provide enhancements to the hedgerow through an understory of lower plantings, and plant wildflowers to create a wildlife and pollinator corridor.
Nature Space
Create an accessible space for all users that provides a mix of wetland plantings and new trees. Close proximity to wildlife corridor and wildflower edge allows users to interact with natural environment.
Clapper Bridge
Natural Play Space
Area to include wood chip seating area, tree trunks, logs, boulders and access to the shallow pond end for natural play opportunities.
Drainage from woodland spring, providing water source for pond.
date 03 July, 2021
Excavate pond to provide a range of depths for wildlife. Deeper area should be kept furthest from the seating area, and ensure pond profile results in a gentle slope to allow access to children for natural play and exploration. Avoid ditch and drain inflow to minimise polluted water and silt by strategic re-use of excated soil, but allow outflow with proper elevation design.
Benches and seating areas provided at all three nature areas, made from woodland offcuts to provide continuity of space
Refuge/Quiet Space
Create a more peaceful space accessed via the restored bridge for quiet reflection and watching the world go by.
Visually connect the ‘outdoor rooms’ to encourage social interaction and discourage anti-social behaviour.
Ensure each space has an edge to protect users from the roadway and to create a sense of enclosure. Native hedge planting, or a mix of native shrubs and plants, would need to be maintained and kept at an appropriate height to retain inter-visibility.

## Zone A - Woodland
Colwinston Old Ford Project (COFP) - Zone A - Woodland: Preservation of nature, removal of arboreal issues and provision of access and seating areas.
| Key: | On-going activity | TBC activity | COFP Working Party meetings = review/decision points
| Task Ref | Topic | High Level Task Description | Detailed Task Description | Task Status | Budget Required? | Task Owner (reports to COFP Committee) | Comments & Progress Updates | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022 | 2023 | 2024
| A1 | Birds | Bird Hide | a) Bird survey conducted b) Identify proposed location c) Identify resources & costs (obtain quotes) required d) TBC - arrange & execute build | On-going | £TBC | Clive Francis |  | a & b | c
|  |  | Bird & Owl Boxes locations |  | On-going | £TBC | Clive Francis |  | a & b | c
| A2 | Trees | Woodland Health Survey | a) Contact Sasha Ufnowska (Llais y Goedwig) to progress survey b) Issue comms to publicise survey results (FB, newsletter, noticeboards) | On-going | No | Rhian Cleaver |  | a & b
|  |  | Coed Cymru Survey & labelling | a) Contact Mike Richards to agree survey date b) Trees labelled for felling | On-going | 450 | Julie Lloyd |  | a |  |  | b
|  |  | Tree Felling | a) Contact tree fellers to obtain quote (felling licence required?) b) Approve costs c) Progress tree felling | Pending | £TBC | Julie Lloyd | NB VoG Ecologist (CC) Suggested leave tall stumps & dead wood for insects. |  |  | a & b | c
|  |  | Felled Tree Disposal | a) Felled wood 'tidied up' & stored at Julie's yard b) Wood to be offered for sale to raise funds* *COFP WP may identify some for use in project e.g. seating, table, path chippings or 'bug hotel' | Pending | £TBC | Julie Lloyd | Update on funds raised to Treasurer |  |  |  | a & b
| A3 | Ponds | Woodland Ponds restoration | a) Liaise with Pheasant Acres for advice b) Liaise with Josh Edwards re his availability to support activity c) Landscape area around pond to level the land, control weeds and fill in holes/depressions in woods | On-going | £TBC | Julie Lloyd | Linked to Wetland task B2 | a |  |  | b - c
| A4 | Weeds | Disposal of Balsalm | Burn Himalayan Balsalm and other weeds pulled from 'Balsalm Bash' | Pending | No | Carl Hadley & Brian Morris | Date is TBC when weeds are considered dry.
Activities to consider/progress from 2022
| A4 (cont.) | Weeds | Removal of nuisance plants | a) Identify plants to be removed & disposal approach with Sasha Ufnowska (Llais y Goedwig) &/or Colin Cheeseman (VoG Ecologist) b) Progress weeding & disposal activity | To be agreed | £TBC | TBC | VoG Ecologist recommended: Ivy - leaving ivy unless it's established to the point where it could lead to tree falling Brambles - leaving alone except to clear for path, seating area or pond area. | [6 empty] | a & b
| A5 | Woodland Path | Create path through the woodland | a) Agree path design i.e. route, surface, border, etc. b) Identify any contractor resource required (quotes) c) Progress path creation | To be agreed | £TBC | TBC | - Consider different teams on different sections - Debris can be used to fill holes / depressions in woodland | [7 empty] | a - c
| A6 | Woodland Seating | Add seating/tables/bug hotels | a) Agree seating design i.e. stumps, benches, etc. b) Agree if tables required i.e. picnic/study area c) Agree if 'green bathing' beds are to be added d) Agree seating/table/bed locations e) Agree if 'bug hotels' to be sited (felled tree stumps?) f) Identify any contractor resource required (quotes) g) Secure materials (unless contractor supplies) h) Progress build activity | To be agreed | £TBC | TBC | - Consider school competition to design 'carvings' to be added to seats/beds - Can felled trees be used (see A2)? | [7 empty] | a - h
| A7 | Perimeter Fencing | Add fencing on roadside | a) Agree fencing design, access points & location (VoG consultation) b) Identify if contractor resource is required (quote) c) Secure materials (unless contractor supplies) d) Progress fencing erection | To be agreed | £TBC | TBC | [7 empty] | a - d
| A8 | Information Board | Add Information Board | a) Agree design & information to be displayed (wildlife, trees, etc.) b) Agree location i.e. access point or seating area? c) Identify if contractor resource is required (quote) d) Secure materials (unless contractor supplies) e) Progress board erection | To be agreed | £TBC | TBC | [8 empty] | a - e
| A9 | Locate Well | Locate well shown on old OS maps | a) SME support required e.g. NRW or VoG Ecologist? | To be agreed | No | Ed Lewis | [7 empty] | a
COFP
COFP
COFP
COFP
COFP
COFP

## Zone B - Wetland
Colwinston Old Ford Project (COFP) - Zone B - Restoration of pond area, removal of Himalayan Balsalm and Ash Tree, and installation of seating and path
| Key: | On-going activity | TBC activity | COFP Working Party meetings = review/decision points
| Task Ref | Topic | High Level Task Description | Detailed Task Description | Task Status | Budget Required? | Task Owner (reports to COFP Committee) | Comments & Progress Updates | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022 | 2023 | 2024
| B1 | Watercress | Confirm water cress presence | a) Contact DEFRA to confirm if protected water cress exists or it's common 'fools water cress' b) Publicise report findings to inform concerned locals residents c) Agree any impacts to plan | On-going | No | Julie Lloyd | a) May require VoG Ecologist too All pond digging activity on-hold pending outcome | a - c
| B2 | Pond | Pheasant Acres advice | Liaise with Pheasant Acres for advice | On-going | No | Julie Lloyd | Linked to Woodland task A3 re Pheasant Acres - Meeting to be arranged
|  |  | Pond siting & approach | Liaise with Sasha Ufnowska (Llais y Goedwig) re pond siting & approach | On-going | No | Rhian Cleaver | Meeting to be arranged NB Consider timing around tadpoles!
|  |  | Pond area designs | Create pond designs - a) technical & b) illustrative | On-going | No | a) Carl Hadley b) Julia Olson | Both design drafts submitted for comment - next COFP WP meeting to review
|  |  | Pond schedule of work | a) Schedule created from the above tasks b) Secure materials c) Contact Josh Edwards to schedule in pond digging d) Progress pond restoration | Pending | £TBC | a/b) Owner is TBC c) Julie Lloyd d) Josh Edwards | Schedule to be reviewed by COFP WP |  | a & b |  | c |  | d
| B3 | Weeds | Removal of nuisance plants | a) Decide on approach i.e. what environmentally friendly treatment to use given the proximity to water course b) Progress weeding & disposal activity | On-going | £TBC | a) COFP WP b) Owner is TBC | a) Liaise with Sasha Ufnowska (Llais y Goedwig) &/or Colin Cheeseman (VoG Ecologist) - use Foam Steam?? Update Peter Evans (via Brian?) | a | b
| B4 | Cultivated Area | Design & develop cultivated seating area | a) Create a design of cultivated area for COFP WP review b) Identify resources required (inc. quotes) c) Implement the cultivated area | Pending | £TBC | Cynthia Gibb | Q. Does task B4 follow task B3? | a & b | c
| B5 | New Willow Trees | Obtain & plant new willow trees | a) Colin Cheeseman (VoG Ecologist) has recommended suitable willow varieties b) Identify local nursaries to supply mature specimens (quotes) c) Obtain funding to purchase & plant the trees (see notes) d) Plant trees per approved design (see task B2) e) Unveiling ceremony to celebrate Queen's 75th B'day | On-going | 1000 | Owner is TBC | c) COFP WP to submit an application for Strong Communities Grant Fund by 19th July, decision expected late Aug. NB Vale Ecologist (CC) recommends winter planting e) NB Tasks B2 & B6 may not be complete when trees planted - delay ceremony? | a & b | c |  |  | d & e
| B6 | Wetland plants | Obtain & plant new wetland plants | a) Colin Cheeseman (VoG Ecologist) has recommended suitable wetland plants b) Confirm planting season with Colin c) Identify local nursaries to plants (quotes) d) Planting | On-going | £TBC | Rhian Cleaver | d) Planting could be in Winter for Spring or in Spring for Summer NB Consider longer term maintenance when choosing plants. | a | b & c |  |  | d
| B7 | Balsalm Bash revisited | Inspection & removal of any returning Balsalm | Potentially organise anoth 'Balsalm Bash' if the plants reappear | Pending | No | Rhian Cleaver | Publicise using FB & Newsletter
COFP
COFP
COFP
COFP
COFP
COFP
COFP
COFP
CEREMONY
COFP

## Zone C - Hedge
Colwinston Old Ford Project (COFP) - Zone C - Hedge laying and create a path in between the hedge and the stream
| Key: | On-going activity | TBC activity | COFP Working Party meetings = review/decision points
| Task Ref | Topic | High Level Task Description | Detailed Task Description | Task Status | Budget Required? | Task Owner (reports to COFP Committee) | Comments & Progress Updates | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022 | 2023 | 2024
| C1 | Hedge Laying | Hedge Laying with Cardiff Conservation Group | a) Contact Sasha Ufnowska (Llais y Goedwig) to obtain details of Cardiff Conservation Group b) Contact Cardiff Conservation Group c) Agree 'hedge laying' approach & dates with Sasha & CCG d) Progress hedge laying | On-going | £TBC | a & c) Rhian Cleaver & b & c) Ed Lewis d) COFP WP | c) Publicise event locally (Fb, newsletter) as job size requires many hands d) May need to lay on refreshments for CCG volunteers | a - c | d
| C2 | Hedge Waste | Disposal of hedge laying waste | a) Identify means of mulching hedge debris b) Identify location to store mulch until needed for hedge path (or woodland path - see task A5?) c) Progress mulching & storage | Pending | £TBC | Julie Lloyd |  |  |  | a & b | c
| C3 | Hedge Path | Create path alongside hedge | a) Agree path design i.e. route, surface (mulch - see task C2?), border, etc. b) Identify contractor resource to clear (concrete blocks/stones) & level the land (quotes) c) Remove stones/concrete blocks in the vacinity d) Progress path creation | Pending | £TBC | a) Carl Hadley & Julia Olson? b) Julie Lloyd c) Contractor d) Owner is TBC | a) Can designs from task B2 incorporate this too? c) Consider any health & safety concerns given alongside stream |  |  | a & b | c
Activities to consider/progress from 2022
| C4 | Dredge Stream | Clear debris from stream | Contact National Resources Wales (NRW) / Welsh Water to confirm who is responsible and confirm if this action is feasible | To be agreed | £TBC | Owner is TBC | Activity may reside solely with responsible authority
COFP

## Zone D - Well
Colwinston Old Ford Project (COFP) - Zone D - Michaelmas Well restoration
| Key: | On-going activity | TBC activity | COFP Working Party meetings = review/decision points
| Task Ref | Topic | High Level Task Description | Detailed Task Description | Task Status | Budget Required? | Task Owner (reports to COFP Committee) | Comments & Progress Updates | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022 | 2023 | 2024
| D1 | Clean the well | Drain and clean the well | Contractor already commissioned. | On-going | £TBC | Carl Hadley | June-21: CH feedback - re-fills after 5 hours so unable to clean the well at present. Should this task be closed? COFP WP to decide.
| D2 | New wall | Complete the perimeter wall around the well | a) Identify source of matching stones b) Identify contractor to build wall c) Cut back weeds d) Create & review design (COFP WP) e) Build/complete well wall | On-going | 10000 | Carl Hadley | b) Out to tender c) Technical design created by Carl | b - d | e
COFP
COFP
COFP

## Zone E - Clapper Bridge
Colwinston Old Ford Project (COFP) - Zone E - Clapper Bridge restoration
| Key: | On-going activity | TBC activity | COFP Working Party meetings = review/decision points
| Task Ref | Topic | High Level Task Description | Detailed Task Description | Task Status | Budget Required? | Task Owner (reports to COFP Committee) | Comments & Progress Updates | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022 | 2023 | 2024
| E1 | Weeds | Removal of nuisance plants | a) Progress weeding & disposal activity b) Measure area then obtain weed-proof membrane, plastic tiles & aggregate c) Lay membrane, tiles & aggregate | On-going | TBC | a) Carl Hadley b & c) Julie Lloyd | b) Membrane & tiles expected to be sourced locally for free by Ray Stokes! Local quarry & villagers to be approached re availability of free aggregate or donation of purchase. | a - c
| E2 | Bridge Path | Create path from clapper bridge to memorial bench | a) Create design b) Review/approve design at COFP WP meeting c) Obtain materials - see task E1 (b) above d) Progress path construction | Pending | TBC | Owner is TBC |  | a
| E3 | Memorial bench | Build & install memorial bench | a) Contractor to be engaged (quotes) b) Dedication message to be added c) Bench build and installation | Pending | TBC | Non Bates | Non on holiday until end of Aug-21 |  |  | a - c
| E4 | New wall | Retaining wall restoration (reclaim land next to Old Parsonage) | a) Engage contractor (quotes) b) Clear area of weeds and brambles c) Source matching stones d) Contractor build | Pending | TBC | Owner is TBC |  |  | a - d
| E5 | Opening Ceremony | Organise Clapper Bridge opening ceremony | a) Agree date and publicise (FB, newsletter, notice boards) b) Agree on dignitary/celebrity to 'cut the ribbon' c) Agree on format i.e. are refreshments required (budget)? d) Prepare event e) Celebrate!! | On-going | TBC | Owner is TBC | Event timing linked to completion of tasks E1 to E4 | a-c | d
COFP
COFP
COFP
CEREMONY