## Slide 1
Cromarty & District Community Council
Update on East Quayside Development Nigg
as at 23 May 21
All permissions for the 225m long quay have been granted.
Land-based work will happen between 0800-1900 Monday-Friday and 0800-1300 on Saturdays. Marine-based work will happen between 0700-1900 Monday-Friday and 0700-1300 on Saturdays.
Dredging within the Cromarty Firth is permitted 24/7.
Construction was due to start the week commencing 19th April 2021 and finish in 14 months.
Dredging and the construction of a temporary causeway started on Monday 19th April 21.
Piling will start in June 2021 and finish in November 2021 – this will be noisy and noise monitoring will happen during the test pile, which will be conducted between 1st-3rd June.
Update regarding the test pile - they will use a vibro-hammer to drive the tube initially and then use an impact hammer.
Noise monitoring will be conducted during the test pile in accordance with their environmental management plan.